November Update

Progress:

Since the start of the semester (weeks 1-5), project tasks included communicating with my supervisor on the aims and objectives to create the project plan, design a rounded risk assessment and declare ethics. Since the submission of the project plan, which included a Gantt chart, block diagram, and decomposed schedule, I have submitted and received the first components order. As the components took 3 weeks to arrive, I revised the circuit connections, created a lab schedule/logbook, and practiced my coding skills in the meantime.

Currently my tasks from weeks 6-7 (once components arrived) include testing the sensors, LCD, microcontrollers, and developing code for each subsystem. This is paired with developing the website for real time data and box design for prototype 1.

From week 7 to week 12, my main tasks include ordering new components order and further web development to ensure its functional by the end of the semester. Other tasks include the final parts of prototype 1 such as 3d printing the components for the ventilator system, laser cut box design, and soldering.

Achievements:

Major achieved since the project plan include the testing of each sensor and getting positive results alongside the data display. Further achievements include understanding how to use Raspberry Pi’s better and project management with allocating time to each task for efficient organisation.

Delays:

A delay that slowed progress was that the heart rate module I wanted was out of stock by the time the technicians ordered it, meaning I couldn’t do any work on heart rate or blood oxygen until the heart rate sensor arrive sin the second components order (predicted week 8). Other delays include the lab desktops being unable to install the Raspberry Pi IDE alongside with the initial components order taking longer then expected to arrive.

Plan Accuracy:

The project plan is still majority accurate a couple of the connections have changed as instead of the Pico W controlling the sensors and motor, it will only control the sensors while the Pico H handles the motor system, while couple of the task have changed week allocation due to delays.

Overall Progress:

The past few weeks have been the bedrock of the project in setting up the sensors, display, and website for prototype 1. This creates the foundation for the final prototype which builds and optimising all the work I’ve currently done.