## Sheet1
| Semester 1 | [5 empty] | Weeks
ID | Tasks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1.01 | Weekly Project Meetings
1.02 | Project Research for Project Plan
1.03 | Submit the Project Plan, Ethics, and RA
1.04 | Submit Intial Components Order
1.05 | Setup & Test for Initial Raw Heart Rate Data
1.06 | Setup & Test for Initial Raw Blood Oxygen Data
1.07 | Setup & Test for Initial Raw Tempurature Data
1.08 | Setup & Design the ventilator with the motor
1.09 | Setup & Test for Initial Raw Air Pressure data | [12 empty] | E9C386
1.1 | Design the Initial Interface of the Website | [12 empty] | BD6060
1.11 | Connect the Website to Device for Data Transfer | [12 empty] | DA895A
1.12 | Combine subsystems for the Combined System | [12 empty] | AC94F4
1.13 | Design the box/body for the Combined System | [12 empty] | b8c19c
1.14 | Integrate the system for the Initial Prototype
1.15 | Crowdfundng Pitch
Semester 2
ID | Tasks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
2.01 | Weekly Project Meetings
2.02 | Initial Design Evaluation for Optimisation
2.03 | Venitlator System Optimisation
2.04 | Air Pressure System Optimisation
2.05 | Data Transfer Optimisation
2.06 | Website Redesign
2.07 | Blood Oxygen System Optimisation
2.08 | Heart Rate System Optimisation
2.09 | Temperature System Optimisation
2.1 | Box Redesign
2.11 | Subsystem integration for the Final Design
2.12 | Poster Research and Preperation
2.13 | Poster Printing
2.14 | Project Abstract Document Submission
2.15 | Bench Inspection Preperation
2.16 | Bench Inspection
2.17 | Final Specification Report
| Year Long | Sem 1 |  |  |  | Sem 2
| Tasks | W1-3 | W4-6 | W7-9 | W10-12 | W1-3 | W4-6 | W7-9 | W10-12
Submission of Initial Documentation
Initial Component tests for Raw Data
Integrating Components for Medical Data
Setting up Data Transfer and Website
Designing the Initial Prototype
Crowdfunding Pitch
Design Evaluation
Update each Subsystem
Create the poster
Bench Inspection
Final Specification Report